## Sheet1
Risk Chart
Revised Assessment after Mitigation
Objective | Risk | Likelihood | Severity | Risk Factor | Risk Mitigation | Consequence Mitigation | Likelihood | Severity | Risk Factor
Complete Project Report | Time constraints due to inaccurate time estimations | 2 | 5 | 10 | To stop myself from running out of time writing the final report, I will complete a rough version of the report alongside building my project. I have also dedicated time at the end of every week to work on the final report and time at the completion of every major objective to complete the report for that section. | If I do run out of time writing my report I could put less emphasis on some of the latter objectives such as Objective 6. Since the most important objectives are completed at the beginning of the project, this should mean that the most important parts of the write-up are also completed at the beginning. Putting less effort inot the latter objectives should not effect the project too badly. | 1 | 3 | 3
Complete Prototype | Time constraints due to inaccurate time estimations | 2 | 5 | 10 | To stop myself from running out of time designing, implementing and testing the prototype for the game, I will build the most vital parts of the prototype first. This can be seen in my build plan. | If I do run out of time building the prototype, I can simply remove some functionality from the latter objectives, such as objective 6. This objective specifically doesn’t offer much in the way of answering my problem to be solved. Removing this will not massively impact my project. | 2 | 3 | 6
Main objective of the project, to create a first-person stealth level. | Lack of end-user engagement. It may be a risk to my project as a whole if end-users do not engage with my prototype. The main beneficiaries of my project are other developers who are working on an FPS stealth level. However, if end-users do not engage with my prototype, those developers may be reluctant to adopt and build upon my prototype. | 2 | 4 | 8 | To mitigate this risk, I will have some user testing mid-way through the development plan after the first 2-3 objectives are complete. If users engage with the prototype at this stage, then I can continue as normal. However, if they are unengaged with the prototype, then I can implement their feedback into the most vital parts of the game. This would also mean I probably would not have the time to develop some latter objectives to their fullest potential but this is ok as the most vital objectives are completed at the start. | If end-users are not satisfied with my completed prototype, then there is not much I can do with the limited time I will have left at that stage of the project. However, if I had more time to complete the project I could make a few more iterations of the prototype based on user feedback. | 1 | 3 | 3
Complete Prototype | Poor code quality. One beneficiary of my project is other developers who may want to take my prototype and use it to build a full game. However, if the quality of my code is not up to scratch then it may dissuade them from picking up the project due to the added time and energy it would take to figure out what my code does or to fix any errors or issues in the code. | 2 | 3 | 6 | To mitigate this risk, I will adhere to good coding standards from some of the technical sources I have listed in the "Problem to be solved" section of my PDD. I will also ensure that I comment on my code as I'm working on it to ensure there are no sections I have forgotten to explain. I will also systematically check every piece of code to ensure there are no errors within the code. | If there is some poor code within my project then I will be unaware until a developer tries to use the code for themselves. However, if I had more time and resources for my project then I could perform regular code reviews every month or so or ask an unbiased 3rd party to review my code for me. Obviously, this is out of the scope of this project. | 2 | 2 | 4
Complete Prototype and Project Report | Poor productivity on the project as a whole form me. | 2 | 5 | 10 | To mitigate this risk, I have set aside time every week to allow me to work on my other module IN3005, so that my work on that module does not interfere with this project. Also, within my build plan I have left some leeway at the end of the project to allow me to catch-up with my objectives if i fall behind at any point. | If my productivity during this project does negatively affect the project as a whole then I can reduce the complexity and put less emphasis on the latter objectives. I have designed my build plan so that the most important objectives are completed first so the objectives at the end are not vital to the success of my project. | 1 | 3 | 3
Complete Prototype | Unfamiliarity with Unity and C# | 2 | 3 | 6 | I will use the hundreds of Unity tutorials online to help me throughout my project | I should be able to do enough with my own knowledge of Unity and the online tutorials such that the number of features I cannot implement are minimal | 1 | 3 | 3
Other coursework | I may be delayed completing coursework for IN3005 that may take away time for this project | 2 | 5 | 10 | I will start the CW for IN3005 early and aim to complete it long before it is due, to give me time to focus on this project | Since the main parts of the project are completed at the start, I could simply put less emphasis on the latter objectives such as objective 6 | 1 | 4 | 4