## Sheet1
Risk Chart
Objective Number | Objective | Risk | Likelihood | Severity | Risk Factor | Risk Mitigation | Consequence Mitigation
n/a | Complete Entire Project | Time constraints for overall project | 2 | 5 | 10 | To mitigate this risk I have placed the most important objective of the project at the beginning and the least important at the end | Since the main parts of the project are completed at the start, I could simply put less emphasis on the latter objectives such as objective 6
n/a | Complete the implementation of the game level in Unity | Unfamiliarity with Unity and C# | 2 | 3 | 6 | I will use the hundreds of Unity tutorials online to help me throughout my project | I should be able to do enough with my own knowledge of Unity and the online tutorials such that the number of features I cannot implement are minimal
n/a | Project Report | Unable to complete the report to good standard in time for submission | 2 | 5 | 10 | I will complete my report alongside every feature I implement and spend time every weekend from now until the submission ensuring the report is up to date. This can be seen in my Gantt chart. | Since the main parts of the project are completed at the start, I could simply put less emphasis on the latter objectives such as objective 6
n/a | Other coursework | I may be delayed completing coursework for IN3005 that may take away time for this project | 2 | 5 | 10 | I will start the CW for IN3005 early and aim to complete it long before it is due, to give me time to focus on this project | Since the main parts of the project are completed at the start, I could simply put less emphasis on the latter objectives such as objective 6
1a | Design and Implement a behaviour tree for the AI | Difficulty implementing a behaviour tree | 3 | 3 | 9 | I aim to use online tutorials in order to help me with this feature | I could use a finite state machine which should be a lot easier to implement
1b | Design and implement a pathfinding algorithm for the enemies to search for the player | Difficulty implementing a pathfinding algorithm | 3 | 2 | 6 | I aim to use online tutorials in order to help me with this feature | I could make the AI search the area randomly and not use a pathfinding algorithm
1c | Design and implement a system that allows the player to be slowly detected by the enemy | Difficulty implementing a detection system that is forgiving to the player and gives the player a chance to move away and not be identified by the enemy | 3 | 3 | 9 | I can split the enemy's cone of vision into separate areas that detect the player slower based on what part of the cone they are in contact with. Eg. If the player is in the enemy's peripheral vision, the detection will go 3x slower than if they are right in front of the player | I could use a binary detection system, that simply goes into Attack mode if the player intersects the enemies cone of vision
2a | Design and implement an icon that allows a player to determine the enemies the current state | UI does not give the player enough information | 3 | 2 | 6 | If I have time left at the end of the project, I can implement more features to give the player more information. This could include a UI element to let the player know where they were last spotted by an enemy. Some games use a ghostly figure of the player to show this. | I could develop some more features to add to the UI at the end of the project
2b | Design and implement a UI element that allows the player to determine how close they are to being spotted | I may not be able to find a suitable sprite/asset for the visual for this feature | 2 | 3 | 6 | I should work on finding assets early so that I know if they are available or not. If they arent, it will give me more time to design a simple asset myself. | I could design a simple version myself
3a | Design and implement 2 stealth mechanics/gadgets the player can use | Difficulty finding assets and animations for the 2 stealth mechanics | 4 | 3 | 12 | I should work on finding assets early so that I know if they are available or not. If they arent, it will give me more time to design a simple asset myself. | I could develop the game without fancy animation as I don’t think that is the main purpose of this project
3b | Design an implement a limitation to the number of times the player can use the mechanic | It may be hard to find a good balance between allowing the player to play the way they want to play and not letting them abuse one mechanic to make the game too easy | 1 | 1 | 1 | I could use the balance in other well-known Third-Person stealth games | I could go without finding the perfect balance and just find a simple balance that works the majority of the time. It should not affect the project massively
4a | Design an implement a unique way the player can traverse the level | I may not be able to find the animations to support this feature | 3 | 2 | 6 | I should work on finding assets early so that I know if they are available or not. If they arent, it will give me more time to design a simple asset myself. | I could develop the game without fancy animation as I don’t think that is the main purpose of this project
5a | Design and implement a cohesive balance between the player's and enemies` health and damage | It may be time consuming finding this balance | 2 | 1 | 2 | I could use the balance in other well-known Third-Person stealth games | I could go without finding the perfect balance and just find a simple balance that works the majority of the time. It should not affect the project massively
5b | Design and implement a cohesive balance for the players weapons | It may be time consuming finding this balance | 2 | 1 | 2 | I could use the balance in other well-known Third-Person stealth games | I could go without finding the perfect balance and just find a simple balance that works the majority of the time. It should not affect the project massively
5c | Design and implement the player`s health system and ensure it does not regenerate | This could have a design risk in that the player may find the level too difficult if they only have a limited amount of health | 1 | 1 | 1 | If I have time at the end of the project, I could add a limited number of health packs to the level. | I could add some health packs at the end of development if I have time. Not doing so will not affect the project massively
6a | Design and implement a main menu and a pause menu | I may run out of time before I can complete this feature | 2 | 2 | 4 | I could use an online tutorial to design a very generic menu system | A simple implementation of this using a tutorial will not affect the project
6b | Design and implement some audio and visual fx that make the game more immersive | This feature may not be very detailed due to time constraints at this stage of the project | 2 | 2 | 4 | I could add small sounds such as footsteps and visuals such as guns firing as and when I implement them into my game. | A simple implementation of this will not affect the project
6c | Design and implement features to allow the player to save and load games | This feature may be too time consuming to implement | 2 | 2 | 4 | I could follow an online tutorial to make a generic version of this feature in my game | A simple implementation of this using a tutorial will not affect the project
108