## Sheet1
Gantt Chart for Individual Project
*Insert Game Title*
[5 empty] | February | [16 empty] | March | [30 empty] | April | [29 empty] | May
[5 empty] | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Task Number | Task Description | Completed? | Start Date | End Date | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
BUILD 1
1ai | player walk, run, jump, crouch
1aii | player shoot
1aiii | player damage upon enemy hit
1avii | player uses throwables
1bii | player aims down sights
2ai | 3 buildings (excluding building 0)
2aiv | 4 basic enemies
3b | small enemy specifics
3c | medium enemy specifics
3d | strong enemy specifics
3e | boss specifics
5aiii | visual fx for gun fired (both player and enemy)
7aiii | HUD displays mini map
7aiv | HUD displays compass
7av | HUD displays crosshair for different weapons
8a | music for each building + ambience for street level
8bi | sound fx for guns firing
8bvii | footstep audio
9ai | checkpoints after every floor
9aii | revert to checkpoints upon death
9aiii | game saves
9avi | game pause + pause menu
9aviii | display set of controls
9aix | display start menu and end card
5av | visual for throwable explosion
8bx | audio for throwable explosion
BUILD 2
1aiv | player takes fall damage
1av | player can shoot variety of guns
1avi | player can pick up new guns
1aix | player can pick up ammo
2aii | implement 4th building (snipers)
2av | 2 hidden map secrets
4ai | xp for kill
4aii | xp for opened chest
4aiii | 5 player levels
4aiv | level up based on xp
4av | recieve unlocks after every level
5ai | hitmarker visual
6ai | ammo dropped on kill chance
6aii | weapon dropped on kill chance
7ai | HUD displays player level
7avi | HUD disappears when ADS
8bii | sound fx for hitmarkers
8biv | sound fx when player takes damage
8bix | character voice clips to help player
9aiv | high scores table
2aiii | loot chests
6bi | chests drop ammo
BUILD 3
1aviii | design and implement weapon wheel
1bi | player slows after taking damage
5aii | different hitmarker visual for headshots
5aiv | level up visual
6bii | additional chest drops on chance
7aii | HUD displays ammo on current gun
8biii | different hitmarker sound on headshot
8bv | sound fx hen player levels up
8bvi | spontaneous noise from enemies when talking
8bviii | footsteps silenced when crouching
9av | fastest time record table
9avii | acheivements