## Sheet1
Gantt Chart for Individual Project
*Insert Game Title*
[5 empty] | February | [16 empty] | March | [30 empty] | April | [29 empty] | May
[5 empty] | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Task Number | Task Description | Completed? | Start Date | End Date | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
BUILD 1
3ai | player walk |  | 2023-02-12 | 2023-02-12 | March 1: Targeted Build 1 Finish; March 16: Latest Build 1 Finish
3aii | player run |  | 2023-02-12 | 2023-02-12 | bar: February 12
3aiii | player jump |  | 2023-02-12 | 2023-02-12 | bar: February 12
3aiv | player crouch |  | 2023-02-12 | 2023-02-12 | bar: February 12
8ai | implement pistol |  | 2023-02-13 | 2023-02-13 | bar: February 13
8aiii | implement AR |  | 2023-02-13 | 2023-02-13 | bar: February 13
8bi | implement small ammo |  | 2023-02-13 | 2023-02-13 | bar: February 13
8bii | implement medium ammo |  | 2023-02-13 | 2023-02-13 | bar: February 13
3av | player shoot |  | 2023-02-13 | 2023-02-14 | bar: February 13 to February 14
9ai | implement grenade |  | 2023-02-14 | 2023-02-14 | bar: February 14
3avi | player throw |  | 2023-02-14 | 2023-02-14 | bar: February 14
5ai | small enemy weapons |  | 2023-02-14 | 2023-02-15 | bar: February 14 to February 15
5aiii | small enemy damage |  | 2023-02-15 | 2023-02-15 | bar: February 15
5aiv | small enemy speed |  | 2023-02-15 | 2023-02-15 | bar: February 15
5av | small enemy health |  | 2023-02-15 | 2023-02-15 | bar: February 15
5avi | small enemy AI |  | 2023-02-15 | 2023-02-16 | bar: February 15 to February 16
5bi | medium enemy weapons |  | 2023-02-16 | 2023-02-16 | bar: February 16
5bii | medium enemy damage |  | 2023-02-16 | 2023-02-16 | bar: February 16
5biii | medium enemy speed |  | 2023-02-16 | 2023-02-16 | bar: February 16
5biv | medium enemy health |  | 2023-02-16 | 2023-02-17 | bar: February 16 to February 17
5di | boss charge attack |  | 2023-02-17 | 2023-02-17 | bar: February 17
5dii | boss ranged attack |  | 2023-02-17 | 2023-02-17 | bar: February 17
5dv | boss damage |  | 2023-02-17 | 2023-02-18 | bar: February 17 to February 18
5dvi | boss speed |  | 2023-02-17 | 2023-02-18 | bar: February 17 to February 18
5dvii | boss health |  | 2023-02-17 | 2023-02-18 | bar: February 17 to February 18
3c | player health |  | 2023-02-18 | 2023-02-18 | bar: February 18
3aix | player damage |  | 2023-02-18 | 2023-02-18 | bar: February 18
4ai | 3 buildings (enemies in 2) |  | 2023-02-18 | 2023-02-20 | bar: February 18 to February 20
4av | different music for each building |  | 2023-02-20 | 2023-02-20 | bar: February 20
4avi | different lighting for each building |  | 2023-02-20 | 2023-02-21 | bar: February 20 to February 21
10ai | hitmarker |  | 2023-02-21 | 2023-02-22 | bar: February 21 to February 22
10aiii | gun fire visuals |  | 2023-02-22 | 2023-02-22 | bar: February 22
10aiv | explosions visuals |  | 2023-02-22 | 2023-02-22 | bar: February 22
10avi | visual for player damage taken |  | 2023-02-22 | 2023-02-23 | bar: February 22 to February 23
11ai | hitmarker sound |  | 2023-02-22 | 2023-02-23 | bar: February 22 to February 23
11aiii | gun fire sound |  | 2023-02-22 | 2023-02-23 | bar: February 22 to February 23
11aiv | explosion sound |  | 2023-02-22 | 2023-02-23 | bar: February 22 to February 23
12aii | HUD displays mini-map |  | 2023-02-23 | 2023-02-24 | bar: February 23 to February 24
12aiii | HUD displays compass |  | 2023-02-24 | 2023-02-24 | bar: February 24
12aiv | HUD displays current weapon |  | 2023-02-24 | 2023-02-24 | bar: February 24
12av | HUD displays current ammo |  | 2023-02-24 | 2023-02-24 | bar: February 24
12avi | HUD displays crosshairs |  | 2023-02-24 | 2023-02-24 | bar: February 24
13ai | checkpoints |  | 2023-02-24 | 2023-02-25 | bar: February 24 to February 25
13aii | revert to checkpoints on death |  | 2023-02-25 | 2023-02-25 | bar: February 25
13avi | start menu |  | 2023-02-25 | 2023-02-26 | bar: February 25 to February 26
13avii | pause menu |  | 2023-02-25 | 2023-02-26 | bar: February 25 to February 26
13aix | controls displayed |  | 2023-02-25 | 2023-02-26 | bar: February 25 to February 26
13ax | end card |  | 2023-02-25 | 2023-02-26 | bar: February 25 to February 26
1a | Challenge write-up |  | 2023-02-27 | 2023-02-28 | bar: February 27 to February 28
1b | Goals write-up |  | 2023-02-27 | 2023-02-28 | bar: February 27 to February 28
1c | Constraint write-up |  | 2023-02-27 | 2023-02-28 | bar: February 27 to February 28
1e | Punishment write-up |  | 2023-02-27 | 2023-02-28 | bar: February 27 to February 28
BUILD 2 | bar: March 1 to March 3
3avii | player ADS |  | 2023-03-04 | 2023-03-04 | March 23: Targeted Build 2 Finish; April 11: Latest Build 2 Finish
3ax | player fall damage |  | 2023-03-04 | 2023-03-04 | bar: March 4
3ad | player health regen |  | 2023-03-04 | 2023-03-05 | bar: March 4 to March 5
4aii | puzzle building |  | 2023-03-05 | 2023-03-07 | bar: March 5 to March 7
4b | 4th sniper building |  | 2023-03-07 | 2023-03-09 | bar: March 7 to March 9
5aii | small enemy rocket launcher |  | 2023-03-09 | 2023-03-09 | bar: March 9
5bv | medium enemy AI |  | 2023-03-09 | 2023-03-10 | bar: March 9 to March 10
5c | heavy enemy |  | 2023-03-10 | 2023-03-11 | bar: March 10 to March 11
5diii | boss heavy and slow attack |  | 2023-03-11 | 2023-03-11 | bar: March 11
5div | boss quick and light attack |  | 2023-03-11 | 2023-03-11 | bar: March 11
6 | progression |  | 2023-03-11 | 2023-03-13 | bar: March 11 to March 13
7 | loot |  | 2023-03-13 | 2023-03-15 | bar: March 13 to March 15
3aviiii | player pick up loot |  | 2023-03-15 | 2023-03-15 | bar: March 15
4aiii | building chest locations |  | 2023-03-15 | 2023-03-15 | bar: March 15
8aii | implement SMG |  | 2023-03-15 | 2023-03-16 | bar: March 15 to March 16
8aiv | implement Sniper |  | 2023-03-16 | 2023-03-16 | bar: March 16
8av | implement Rocket Launcher |  | 2023-03-16 | 2023-03-16 | bar: March 16
8biii | implement sniper ammo |  | 2023-03-16 | 2023-03-17 | bar: March 16 to March 17
8biv | implement rocket ammo |  | 2023-03-16 | 2023-03-17 | bar: March 16 to March 17
9aii | implement molotov cocktails |  | 2023-03-16 | 2023-03-17 | bar: March 16 to March 17
10aii | different visual hitmarker for headshots |  | 2023-03-17 | 2023-03-18 | bar: March 17 to March 18
10av | visual for levelling up |  | 2023-03-18 | 2023-03-18 | bar: March 18
11aii | different sound hitmarker for headshots |  | 2023-03-18 | 2023-03-18 | bar: March 18
11av | sound for levelling up |  | 2023-03-18 | 2023-03-18 | bar: March 18
11avi | sound when player health is low |  | 2023-03-18 | 2023-03-19 | bar: March 18 to March 19
11avii | footstep audio |  | 2023-03-19 | 2023-03-19 | bar: March 19
12ai | HUD displays players level |  | 2023-03-19 | 2023-03-19 | bar: March 19
13aiii | game saves |  | 2023-03-19 | 2023-03-20 | bar: March 19 to March 20
13aiv | high score table |  | 2023-03-20 | 2023-03-20 | bar: March 20
1d | Reward write-up |  | 2023-03-21 | 2023-03-22 | bar: March 21 to March 22
1f | Flow write-up |  | 2023-03-21 | 2023-03-22 | bar: March 21 to March 22
1g | Feedback write-up |  | 2023-03-21 | 2023-03-22 | bar: March 21 to March 22
1h | Storytelling write-up |  | 2023-03-21 | 2023-03-22 | bar: March 21 to March 22
BUILD 3 | bar: March 23 to March 25
3axi | weapons wheel |  | 2023-03-26 | 2023-03-27 | April 4: Targeted Build 3 Finish; April 21: Latest Build 3 Finsh
3b | player slows after taking damage |  | 2023-03-27 | 2023-03-28 | bar: March 27 to March 28
4aiv | secret loot locations |  | 2023-03-28 | 2023-03-28 | bar: March 28
8c | headshot multiplier |  | 2023-03-28 | 2023-03-29 | bar: March 28 to March 29
11aviii | footstep audio silenced when crouched |  | 2023-03-29 | 2023-03-30 | bar: March 29 to March 30
11aix | enemy speaking noise |  | 2023-03-30 | 2023-03-31 | bar: March 30 to March 31
13v | fastest time table |  | 2023-03-31 | 2023-04-01 | bar: March 31 to April 1
13viii | acheivements |  | 2023-04-01 | 2023-04-03 | bar: April 1 to April 3