## Sheet1
Objective Num | Objective | Risk | Likelihood | Severity | Risk Mitigation | Consequence Mitigation
n/a | General models and animations | I cannot find models or animations that fit well within my game | 2 | 2 | I can start looking for models early so that if I can't find a model close to what I'm looking for, I can quickly change a small detail in the premise of my game to accommodate for a model/animation I can find | I can always remove the feature in the worst-case scenario and find a way to implement a replacement feature from a model/animation I have found
n/a | General work in Unity and C# | Unfamiliarity with the Unity engine and C# | 3 | 3 | Try to complete as much of the Unity Programmer pathway on Unity Learn before I begin work | If I'm unfamiliar with how to complete something, I can skip ahead in the tutorials and complete the specific tutorial that will help me complete my current task
n/a | Time Constraints | There is a risk that I have underestimated how long each task will take me while designing my Gantt chart | 3 | 2 | I have tried to leave a lot of time at the end of the project completion and before submission to allow me to catch up on anything that I may not have been able to do within the original allotted time-frame | If I find that a certain feature will take too long, then I can either remove it or remove a feature from build 3 as this won't cause significant damage to my overall grade.
3axi | Design and implement a weapon wheel for the player | It may be too hard to implement a suitable weapon wheel | 3 | 2 | Watch tutorials on the UnityLearn website to see if it has been donw before | I could always have a simple weapon swap system without the need for a complex weapon wheel
3b | Make the player slow down after taking damage | It may be too hard to reduce the players speed specifically after taking damage | 1 | 3 | Watch a tutorial on a Unity FPS game that covers this topic | I could simply omit this feature without much harm to the end product
4a | Design and implement 3 traversable buildings | I may not be able to find a suitable model for these buildings online | 3 | 4 | Check to find models early in development | I would have to design these buildings myself maybe using Blender, I should start this as soon as I find out if I can find the correct models or not
4aii | Puzzle element to one of the buildings | I may not be able to design good puzzles for the second building | 3 | 3 | Try to find good inpiration of puzzles in games | I could change the second building to have something different to change the pace, maybe I could use the second building to tell more of the background story of the game
5 | Implementing 4 different enemies | It may take too long to implement all 4 | 2 | 2 | Design very simple versions of them first and then slowly build on them | I could easily remove 1 enemy type that I didn’t have time to properly implement
5bv, 5cvi, 5cvii | Semi-Intelligent AI for 2 enemy types | It may be too difficult to implement the AI for the enemy types that like to take cover and fight more tactically | 4 | 3 | Design the AI very simply first and then once that works, slowly start to add behaviours to the AI. I could also watch tutorials about AI in Unity | I could just be able to have a simple AI for all enemies
5di,5dii,5diii,5div | Design and Implement 4 different attack for the boss | It may be difficult designing 4 unique attacks | 3 | 2 | Try to find an existing boss model that has a large number of potential attacks | I could make the boss have more health and only have 2 attacks. To try to balance it out a bit more, that attack could get faster as the boss` health drops
11aix | Spontaneous noise from the enemies as if they are talking | It may be difficult to implement this to occur in a way that sounds like conversation | 2 | 1 | Research how it is done in other games and implement the findings into my game | Instead of trying to make it sound like they are talking, I could just have enemy voice clips play randomly to create an ambience
11aviii | Silence footsteps if player is crouching | It may be too difficult to turn down footstep audio specifically when a player is crouching | 2 | 1 | Complete more audio tutorials on Unity Learn | I could just have the footstep audio muted entirely when the player is crouched or just leave the footstep audio the same regardless if the player is crouched or standing.
13ai,13aii | Checkpoints in game | I may find it difficult to create a good checkpoint system in Unity | 3 | 4 | I hope to find some good tutorials online and on Unity Learn about how to set up checkpoint is a Unity Game | If I figure out how to make a simple checkpoint but I can't implement it properly to activate it on every floor of a building, ill just activate the checkpoint after the player leaves every building. If I can't get checkpoints working at all, I can get rid of them entirely and just rely on save games to save the player`s progress.
13aviii | Achievements | I may find it difficult to implement achievements in Unity | 4 | 3 | I hope to find some useful tutorials online and on Unity Learn that can teach me how to implement achievements | If I cannot implement achievements, I will probably have to remove the feature altogether. There is no other way to implement a similar feature that I can think of.
Likelihood: 1 (Very Unlikely) - 5 (Very Likely)
Severity: 1 (Very Insignificant) - 5 (Significant)