## Sheet1
Individual Project
[5 empty] | March | [30 empty] | April
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task Number | Task Decription | Completed? | Start Date | End Date | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
n/a | Final Project Submission | bar: March 24 to March 26; April 1 to April 2; April 8 to April 25
Stealth AI
1a | Design, implement, test and complete the write-up for the stealth AI behaviour tree | bar: March 5 to March 10
1b | Design, implement, test and complete the write-up for the pathfinding algorithm that the AI will use to search for the player | bar: March 3 to March 6
1c | Design, implement, test and complete the write-up for AI being able to detect the player slowly over time. | bar: March 21 to March 23; April 4
1(General) | Complete any remaining pieces of work related to the write-up up until this point. | bar: March 9 to March 12
Stealth UI
2a | Design, implement, test and complete the write-up for the icon above the enemies head, depicting the enemies` current state. | bar: March 13 to March 15
2b | Design, implement, test and complete the write-up for the UI element that lets the player know how close they are to being spotted | bar: March 14 to March 16
2(General) | Complete any remaining pieces of work related to the write-up up until this point. | bar: March 16 to March 17
Stealth Mechanics
3a | Design, implement, test and complete the write-up for 2 different mechanics that aid the player in being stealthy | bar: March 18 to March 23
3b | Design, implement, test and complete the write-up for limiting the mechanics to a finite number of uses within the level | bar: March 22 to March 24
3(General) | Complete any remaining pieces of work related to the write-up up until this point. | bar: March 24 to March 25
Movement/ Traversal
4 | Design, implement, test and complete the write-up for a unique way for the player to traverse the level | bar: March 26 to March 30
Balance
5 | Design, implement, test and complete the write-up for the balance between the player and the enemies. (Includes objective 5a, 5b and 5c) | bar: March 31 to April 4
Other Functionality
6a | Design, implement, test and complete the write-up for a main menu and a pause menu | bar: April 5 to April 6
6b | Design, implement, test and complete the write-up for the audio and visual fx. (e.g. guns firing or footstep audio) | bar: April 6 to April 8
6c | Design, implement, test and complete the write-up for saving and loading the level | bar: April 8 to April 9