## Sheet1
Individual Project | [101 empty] | Code |  |  | Meeting |  |  |  | Final
[5 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task Number | Task Decription | Completed? | Start Date | End Date | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
n/a | Final Project Submission |  | n/a | n/a | bar: March 24 to March 26; April 4; April 15 to April 16; April 21 to April 22; April 29 to April 30; May 4 to May 8; May 13 to May 14; May 20 to May 22; May 27 to May 28; May 30 to May 31
Stealth AI
1a | Design, implement, test and complete the write-up for the stealth AI behaviour tree |  | 2023-04-22 | 2023-05-05 | bar: April 22; April 26 to May 2; May 4 to May 5
1b | Design, implement, test and complete the write-up for the pathfinding algorithm that the AI will use to search for the player |  | 2023-04-04 | 2023-04-21 | bar: April 4; April 14 to April 21
1c | Design, implement, test and complete the write-up for AI being able to detect the player slowly over time. |  | 2023-03-21 | 2023-03-23 | bar: March 21 to March 23
1(General) | Complete any remaining pieces of work related to the write-up up until this point. |  | 2023-03-21 | 2023-05-05 | bar: March 21; April 4; April 21 to April 22; May 4 to May 7
Stealth UI
2a | Design, implement, test and complete the write-up for the icon above the enemies head, depicting the enemies` current state. |  | 2023-05-07 | 2023-05-08 | bar: May 7 to May 8
2b | Design, implement, test and complete the write-up for the UI element that lets the player know how close they are to being spotted |  | 2023-05-09 | 2023-05-11 | bar: May 9 to May 11
2(General) | Complete any remaining pieces of work related to the write-up up until this point. |  | 2023-05-08 | 2023-05-11 | bar: May 8; May 11
Stealth Mechanics
3a | Design, implement, test and complete the write-up for 2 different mechanics that aid the player in being stealthy |  | 2023-05-13 | 2023-05-28 | bar: May 13 to May 28
3b | Design, implement, test and complete the write-up for limiting the mechanics to a finite number of uses within the level |  | 2023-05-29 | 2023-05-31 | bar: May 29 to May 31
3(General) | Complete any remaining pieces of work related to the write-up up until this point. |  | 2023-05-30 | 2023-06-01 | bar: May 13 to May 14; May 30 to June 1
Movement/ Traversal
4 | Design, implement, test and complete the write-up for a unique way for the player to traverse the level | bar: June 2 to June 3
Balance
5 | Design, implement, test and complete the write-up for the balance between the player and the enemies. (Includes objective 5a, 5b and 5c) | bar: June 4 to June 5
Other Functionality
6a | Design, implement, test and complete the write-up for a main menu and a pause menu
6b | Design, implement, test and complete the write-up for the audio and visual fx. (e.g. guns firing or footstep audio)
6c | Design, implement, test and complete the write-up for saving and loading the level
Other Coursework
n/a | IN3005 Coursework |  | n/a | n/a | bar: March 6 to March 12; March 24 to April 3; April 5 to April 13; May 12