## Sheet1
Risk Chart
|  | Assessment |  |  |  |  | Revised Assessment after Mitigation
Objective | Risk | Likelihood | Severity | Risk Factor | Risk Mitigation | Consequence Mitigation | Likelihood | Severity | Risk Factor
Complete Project On Time | Time constraints due to inaccurate time estimations. | 2 | 5 | 10 | To stop myself from running out of time writing the final report, I will complete a rough version of the report alongside building my project. I have also dedicated time at the end of every week to work on the final report and time at the completion of every major objective to complete the report for that section. To stop myself from running out of time designing, implementing and testing the prototype for the game, I will build the most vital parts of the prototype first. This can be seen in my build plan. | If I do run out of time on my project I could put less emphasis on some of the latter objectives such as Objective 6. Since the most important objectives are completed at the beginning of the project, this should mean that the most important parts of the write-up and prototype are also conducted at the beginning. Putting less effort into the latter objectives should not affect the project too badly. | 2 | 3 | 6
Main objective of the project, to create a first-person stealth level. | Lack of end-user engagement. It may be a risk to my project as a whole if end-users do not engage with my prototype. The main beneficiaries of my project are other developers who are working on an FPS stealth level. However, if end-users do not engage with my prototype, those developers may be reluctant to adopt and build upon my prototype. | 2 | 4 | 8 | To mitigate this risk, I will have some user testing mid-way through the development plan after the first 2-3 objectives are complete. If users engage with the prototype at this stage, then I can continue as normal. However, if they are unengaged with the prototype, then I can implement their feedback into the most vital parts of the game. This would also mean I probably would not have the time to develop some latter objectives to their fullest potential but this is ok as the most vital objectives are completed at the start. | If end-users are not satisfied with my completed prototype, then there is not much I can do with the limited time I will have left at that stage of the project. However, if I had more time to complete the project I could make a few more iterations of the prototype based on user feedback. | 1 | 3 | 3
Complete Prototype | Poor code quality. One beneficiary of my project is other developers who may want to take my prototype and use it to build a full game. However, if the quality of my code is not up to scratch then it may dissuade them from picking up the project due to the added time and energy it would take to figure out what my code does or to fix any errors or issues in the code. | 2 | 3 | 6 | To mitigate this risk, I will adhere to good coding standards from some of the technical sources I have listed in the "Problem to be solved" section of my PDD. I will also ensure that I comment on my code as I'm working on it to ensure there are no sections I have forgotten to explain. I will also systematically check every piece of code to ensure there are no errors within the code. | If there is some poor code within my project then I will be unaware until a developer tries to use the code for themselves. However, if I had more time and resources for my project then I could perform regular code reviews every month or so or ask an unbiased 3rd party to review my code for me. Obviously, this is out of the scope of this project. | 2 | 2 | 4
Complete Prototype and Project Report | Poor productivity on the project as a whole from me. | 2 | 5 | 10 | To mitigate this risk, I have set aside time every week to allow me to work on my other module IN3005, so that my work on that module does not interfere with this project. Also, within my build plan I have left some leeway at the end of the project to allow me to catch-up with my objectives if i fall behind at any point. | If my productivity during this project does negatively affect the project as a whole then I can reduce the complexity and put less emphasis on the latter objectives. I have designed my build plan so that the most important objectives are completed first so the objectives at the end are not vital to the success of my project. | 1 | 3 | 3
Complete Prototype | Unfamiliarity with Unity and C# | 2 | 3 | 6 | I will use the hundreds of Unity tutorials online to help me throughout my project | I should be able to do enough with my own knowledge of Unity and the online tutorials such that the number of features I cannot implement are minimal | 1 | 3 | 3
Other coursework | I may be delayed completing coursework for IN3005 that may take away time for this project | 2 | 5 | 10 | I will start the CW for IN3005 early and aim to complete it long before it is due, to give me time to focus on this project | Since the main parts of the project are completed at the start, I could simply put less emphasis on the latter objectives such as objective 6 | 1 | 4 | 4
Complete Project | Consultant Delays. There may be a risk that my consultant for the project is delayed or unavailable to advise me on my project for any given reason. This could lead to me developing work not in line with their requirements. | 2 | 2 | 4 | To mitigate the risk, I will contact my consultant as regularly as I can so that in the event that they are unavailable I still have some relatively recent feedback. | If my consultant is unavailable, I can contact the project team for any short-term guidance or quick queries and I can also consult the project handbook for help. If either of these options has not solved my issues, I can move on to another part of my project and make a note to ask my consultant about the part I was struggling with at the next available opportunity. | 1 | 1 | 1
Complete Prototype | Incomprehensive Testing. There is a risk that if the testing of my project is not up to par then bugs or design flaws may be found by my potential beneficiaries after project completion. This could result in my beneficiaries not building upon my prototype due to the potential underlying issues. | 3 | 3 | 9 | To mitigate this risk, I will systematically test each implementation during the development phase. This fits in line with my agile methodology approach to the project. What this means is, if there is an issue, I will re-develop this part of the prototype and have it working correctly before moving forward. This should hopefully minimize potential errors in my design/implementation. | In the worst-case scenario, I should let potential beneficiaries know that testing was undertaken by myself during development and due to a lack of time and resources, I was unable to perform thorough quality assurance for my prototype. Going forward, if I want to resolve this, I may have to enlist the help of a QA tester but this is not in the scope of this project. | 2 | 3 | 6
Complete Prototype | Scope Creep. There is a risk that during development, I may think of new features that may improve my prototype. However, this can lead to time overruns and creates a risk that I may not complete the essential parts of my project before the deadline. | 2 | 3 | 6 | To mitigate this risk, I will look over the objectives and requirements for the project regularly and ensure not to add features that are not in my project definition. | To mitigate the consequences of this risk, I could shorten the scope of my total project, especially the last few objectives. In my build plan, the objectives that are most important are completed first, so not including the latter objectives in order to meet time constraints should not affect my prototype too badly. | 1 | 2 | 2
Complete Project | Generic Objective Specification. There is a risk that my objectives are not well-defined in the project definition. This could lead to some ambiguity in my design and implementation. | 2 | 3 | 6 | To mitigate this risk, I will ensure that my objectives are well-defined and unambiguous. It is also important that I regularly check the requirements and objectives so that I am always aware of what the end result should look like. | Mitigating the consequences of this risk is quite difficult within the time frame of this project. However, if I did have more time and by the end of my project I had missed my objectives, then I would have to refactor some parts of my prototype to better fit the requirements. | 1 | 3 | 3