## Sheet1
Individual Project | [15 empty] | IN3005 Deadline | [31 empty] | IN3005 Deadline | [30 empty] | IN3005 Deadline | [22 empty] | Code Submission | [6 empty] | Final Report
[5 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Task Number | Task Decription | Completed? | Start Date | End Date | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
n/a | Final Project Submission |  | n/a | n/a | bar: March 24 to March 26; April 4
n/a | IN3005 Coursework |  | n/a | n/a | bar: March 6 to March 12; March 24 to April 3; April 5 to April 13
Stealth AI
1a | Design, implement, test and complete the write-up for the stealth AI behaviour tree | bar: April 22; April 26 to April 30
1b | Design, implement, test and complete the write-up for the pathfinding algorithm that the AI will use to search for the player |  | 2023-04-04 | 2023-04-22 | bar: April 4; April 14 to April 21
1c | Design, implement, test and complete the write-up for AI being able to detect the player slowly over time. |  | 2023-03-21 | 2023-03-23 | bar: March 21 to March 23
1(General) | Complete any remaining pieces of work related to the write-up up until this point. | bar: March 21; April 4; April 21 to April 22
Stealth UI
2a | Design, implement, test and complete the write-up for the icon above the enemies head, depicting the enemies` current state.
2b | Design, implement, test and complete the write-up for the UI element that lets the player know how close they are to being spotted
2(General) | Complete any remaining pieces of work related to the write-up up until this point.
Stealth Mechanics
3a | Design, implement, test and complete the write-up for 2 different mechanics that aid the player in being stealthy
3b | Design, implement, test and complete the write-up for limiting the mechanics to a finite number of uses within the level
3(General) | Complete any remaining pieces of work related to the write-up up until this point.
Movement/ Traversal
4 | Design, implement, test and complete the write-up for a unique way for the player to traverse the level
Balance
5 | Design, implement, test and complete the write-up for the balance between the player and the enemies. (Includes objective 5a, 5b and 5c)
Other Functionality
6a | Design, implement, test and complete the write-up for a main menu and a pause menu
6b | Design, implement, test and complete the write-up for the audio and visual fx. (e.g. guns firing or footstep audio)
6c | Design, implement, test and complete the write-up for saving and loading the level